## MetaFruit
No. | Feature | Function | Main actors | Description | In Charge | RDS | Status | Deadline | Level | LOC | Notes / Updates
1 | Authentication - Sign-up | User Registration Local Form | Guest | Local sign-up form with input validation, BCrypt password hashing, and DB insertion. | HoangDMHE191087 | I.1 | Done | 2026-05-22 | 2 | 90
|  | Google OAuth Sign-up | Guest | Google OAuth sign-up with Callback URL handling and new user creation. | HoangDMHE191087 | I.2 | Done | 2026-05-22 | 3 | 120
|  | Role Selection | Guest | Role selection during sign-up with pending status for Shop Owners. | HoangDMHE191087 | I.3 | Done | 2026-05-22 | 1 | 60
2 | Authentication - Login/Logout | Local Login | All | Local login with email/phone, BCrypt verification, and session storage. | HoangDMHE191087 | I.4 | Done | 2026-05-22 | 2 | 90
|  | Google OAuth Sign-in | All | Google OAuth login with automatic matching and session creation. | HoangDMHE191087 | I.5 | Done | 2026-05-22 | 3 | 120
|  | User Logout | Customer, Shop Owner, Delivery , Admin | Logout handling by clearing session data and redirecting to homepage. | HoangDMHE191087 | I.6 | Done | 2026-05-22 | 1 | 60
|  | Login Lockout | Guest | Account lockout for 15 minutes after 5 consecutive failed login attempts. | HoangDMHE191087 | I.7 | Done | 2026-05-22 | 3 | 120
3 | User Profile Management | View Profile | Customer, Shop Owner, Delivery , Admin | Profile page displaying user details fetched from session and DB. | HoangDMHE191087 | I.8 | Done |  | 2 | 90
|  | Edit Profile | Customer, Shop Owner, Delivery , Admin | Profile editing form with data validation and database update. | HoangDMHE191087 | I.9 | Done |  | 3 | 120
|  | Manage Addresses | Customer | Multiple shipping address management with default address toggle. | HoangDMHE191087 | I.10 | Done |  | 3 | 120
4 | Security - Password | Change Password | Customer, Shop Owner, Delivery , Admin | Change password form with old password verification and BCrypt hashing. | HoangDMHE191087 | I.11 | Done |  | 2 | 90
|  | Reset Password | Customer, Shop Owner, Delivery , Admin | Reset password with send email otp verification and change password | HoangDMHE191087 | III.34 | Done
5 | Security - Access Control | Role Management | System | Role-Based Access Control (RBAC) filter protecting admin/shop/customer paths. | HoangDMHE191087 | I.12 | Done | 2025-05-27 | 4 | 150
6 | Product Discovery | View Product List | Guest, Customer | Paginated active product list displaying name, image, and price. | HoangDMHE191087 | I.13 | Done | 2026-05-22 | 3 | 120
|  | View Product Details (Static) | Guest, Customer | Product details page displaying static info, origin, and expiry. | HoangDMHE191087 | I.14 | Done |  | 2 | 90
|  | Browse by Category | Guest, Customer | Product filtering by category using sidebar or dropdown. | HoangDMHE191087 | I.15 | Done | 2026-05-22 | 1 | 60
|  | Browse Featured Products | Guest, Customer | Featured products section on homepage displaying top 8 items. | HoangDMHE191087 | I.16 | Done |  | 2 | 90
|  | Search by Product Name | Guest, Customer | Product search bar with name wildcard matching and injection prevention. | HoangDMHE191087 | I.17 | Done | 2026-05-22 | 2 | 90
7 | Admin User Management | Manage Customers | Admin | Admin panel: Paginated customer list display and search. | Duong | I.18 | Done |  | 3 | 120
|  | Manage Shop Owners | Admin | Admin panel: Paginated shop owner list and approval tracking. | Duong | I.19 | Done |  | 3 | 120
|  | Block/Unblock Accounts | Admin | Admin control: Block or unblock user accounts instantly. | Duong | I.20 | Done |  | 2 | 90
|  | Approve Shop Owner Accounts | Admin | Admin control: Approve pending Shop Owner accounts to active status. | Duong | I.21 | Done |  | 2 | 90
8 | Product Catalog Management | Add New Product | Shop Owner | Shop Owner: Add new product with image upload and DB insertion. | Khang | II.1 | Done |  | 4 | 150
|  | Edit Product Info | Shop Owner | Shop Owner: Edit product information and update in database. | Khang | II.2 | Done |  | 4 | 150
|  | Delete Listing | Shop Owner | Shop Owner: Soft delete product by updating status to DELETED. | Khang | II.3 | Done |  | 1 | 60
|  | Hide Listing | Shop Owner | Shop Owner: Toggle product visibility (ACTIVE or INACTIVE). | Khang | II.4 | Done |  | 1 | 60
|  | Product Images CRUD | Shop Owner | Shop Owner: CRUD operations for uploading multiple product images. | Khang | II.5 | Done |  | 4 | 150
9 | Product Discovery (Advanced) | View Product Details (Advanced) | Guest, Customer | Dynamic product details page showing variants and slide show. | HoangDMHE191087 | II.6 | Done |  | 4 | 150
10 | Product Customization | Weight Variants | Shop Owner | Shop Owner: Manage weight variants with distinct price and stock. | Hai | II.7 | Done |  | 3 | 120
|  | Packaging Options | Shop Owner | Customer: Select packaging options (gift box, foam) with dynamic pricing. | Hai | II.8 | Done |  | 2 | 90
|  | Organic/Imported Labels | Shop Owner | Display Organic or Imported labels on products dynamically. | Hai | II.9 | Done |  | 1 | 60
|  | Seasonal Availability | Shop Owner | Restrict product ordering to its configured seasonal availability. | Hai | II.10 | Done |  | 3 | 120
11 | Stock & Inventory Control | Stock Quantity Tracking | System | System: Automatic stock deduction on purchase and return on cancellation. | Hai | II.11 | Done |  | 3 | 120
|  | Low Stock Alerts | Shop Owner | Shop Owner: Dashboard alerts for items with low stock quantity. | Hai | II.12 | Done |  | 2 | 90
|  | Restock Management | Shop Owner | Shop Owner: Log replenishment events and update inventory counts. | Hai | II.13 | Done |  | 3 | 120
12 | Pricing Strategy | Base Pricing | Shop Owner | Shop Owner: Set base pricing for each product variant in VND. | Hai | II.14 | Done |  | 2 | 90
|  | Discount Pricing | Shop Owner | Shop Owner: Configure discount prices with slashed original prices. | Hai | II.15 | Done |  | 2 | 90
13 | Advanced Search & Filters | Filter Category | Guest, Customer | Advanced product list filtering by selecting multiple categories. | Hai | II.16 | Done |  | 3 | 120
|  | Filter Price | Guest, Customer | Advanced product list filtering using a price range slider. | Hai | II.17 | Done |  | 3 | 120
|  | Filter Rating | Guest, Customer | Advanced product list filtering by minimum star rating. | Hai | II.18 | Done |  | 2 | 90
|  | Filter Availability | Guest, Customer | Advanced product list filtering to only show in-stock products. | Hai | II.19 | Done |  | 2 | 90
|  | Sort Products | Guest, Customer | Sort products by price, newest arrival, or top rating. | Hai | II.20 | Done |  | 2 | 90
14 | Smart Product Recommendations | Recommended Fruits | Guest, Customer | Recommend similar products from the same category on detail pages. | Hai | II.21 | Done |  | 2 | 90
|  | Best Sellers | Guest, Customer | Homepage section displaying the top 5 best-selling products. | Hai | II.22 | Done |  | 3 | 120
|  | Recently Viewed | Guest, Customer | Display products recently viewed by customer | Hai | II.23 | Done |  | 3 | 120
15 | Shopping Cart System | Guest Cart LocalStorage | Guest | Guest shopping cart system stored locally in browser LocalStorage. | HoangDMHE191087 | II.24 | Done |  | 1 | 60
|  | Customer Cart DB | Customer | Database-backed shopping cart system for registered customers. | HoangDMHE191087 | II.25 | Done |  | 3 | 120
|  | Guest-Customer Cart Sync | Customer | Synchronize guest LocalStorage cart with DB cart upon login. | HoangDMHE191087 | II.26 | Done |  | 4 | 150
|  | Update Quantity | Guest, Customer | Update cart item quantities with live stock checks and price recalculation. | HoangDMHE191087 | II.27 | Done |  | 2 | 90
|  | Remove Product | Guest, Customer | Remove individual items or clear all products from the cart. | HoangDMHE191087 | II.28 | Done |  | 2 | 90
|  | Cart Summary | Guest, Customer | Display cart totals including items, weight, and subtotal. | HoangDMHE191087 | II.29 | Done |  | 2 | 90
16 | Wishlist System | Add to Wishlist | Customer | Customer: Add favorite products to personal wishlist. | Quan | II.30 | To Do |  | 2 | 90
|  | Remove from Wishlist | Customer | Customer: Remove items from wishlist. | Quan | II.31 | To Do |  | 1 | 60
|  | Move Wishlist to Cart | Customer | Customer: Move items from wishlist to shopping cart directly. | Quan | II.32 | To Do |  | 3 | 120
17 | Checkout Process | Select Delivery Address | Customer | Customer: Select shipping address from profile list during checkout. | HoangDMHE191087 | II.33 | Done |  | 2 | 90
|  | Order Confirmation | Customer | Order confirmation page with order ID and payment instructions. | HoangDMHE191087 | II.34 | Done |  | 2 | 90
18 | Order Placement | Create Order | Customer | Customer checkout: Transactional order and order items creation. | HoangDMHE191087 | II.35 | Done |  | 5 | 180
|  | Reservate Inventory | System | System: Hold stock during checkout and rollback if stock is insufficient. | HoangDMHE191087 | II.36 | Done |  | 4 | 150
19 | Customer Order Tracking | Reorder Previous Purchase | Customer | Customer: Quick reordering of items from historical purchases. | HoangDMHE191087 | II.37 | Done |  | 3 | 120
|  | Track Order Status | Customer | Customer: Track live order delivery status using visual timeline. | HoangDMHE191087 | II.38 | Done |  | 3 | 120
|  | Estimated Delivery Time | Delivery, Customer, Shop Owner | Restrict product ordering to its configured seasonal availability. | Duong | II.39 | Done |  | 1 | 60
|  | Order Delivery Confirmation | Customer | Customer: Confirm receipt of order to update status to DELIVERED. | Duong | II.40 | Done |  | 2 | 90
20 | Delivery Staff Flow | View Orders for Delivery | Delivery | Delivery Staff: Dashboard with pending delivery jobs and location filters. | HoangDMHE191087 | II.41 | Done |  | 3 | 120
|  | Update Shipping Status | Delivery | Delivery Staff: Update delivery status to Shipped, Delivered, or Failed. | HoangDMHE191087 | II.42 | Done |  | 2 | 90
21 | Shop/Admin: Order success and cancellation statistics charts. | Approve Order Shop Owner | Shop Owner | Shop Owner: Approve orders and trigger packing process. | Duong | II.43 | Done |  | 3 | 120
|  | Reject Order Shop Owner | Shop Owner | Shop Owner: Cancel orders with a mandatory reason and restock items. | Duong | II.44 | Done |  | 3 | 120
|  | Mark Order as Delivered | Shop Owner, Delivery | Shop Owner/Delivery: Manually mark orders as delivered to close sale. | Duong | II.45 | Done |  | 2 | 90
22 | Content Moderation & Categories | Approve Products | Admin | Admin: Review and approve new product listings to active status. | HoangDMHE191087 | II.46 | Done |  | 3 | 120
|  | Remove Inappropriate Products | Admin | Admin: Block or hide violating product listings from the public. | HoangDMHE191087 | II.47 | Done |  | 2 | 90
|  | Manage Categories CRUD | Admin | Admin: CRUD operations for managing product categories. | HoangDMHE191087 | II.48 | Done |  | 4 | 150
23 | Online Payment Integration | Cash on Delivery COD | Customer | Customer checkout: Support Cash on Delivery (COD) payment option. | HoangDMHE191087 | III.1 | Done |  | 2 | 90
|  | E-wallet VietQR Dynamic QR | Customer | Customer checkout: Dynamic VietQR code generation for instant payments. | HoangDMHE191087 | III.2 | Done |  | 4 | 150
|  | Process Payment | System | System: Handle incoming payment webhook requests with signature validation. | HoangDMHE191087 | III.3 | Done |  | 5 | 180
|  | Payment Confirmation SePay Webhook | System | System: SePay webhook receiver to auto-approve orders on payment. | HoangDMHE191087 | III.4 | Done |  | 6 | 210
|  | Real-time Status Polling | Customer | Customer checkout: Real-time API polling for payment success. | HoangDMHE191087 | III.5 | Done |  | 2 | 90
|  | Payment Refund Logic | Admin | Admin control: Process refunds for cancelled or returned orders. | HoangDMHE191087 | III.6 | Done |  | 4 | 150
24 | Discount Promotion Engine | Apply Coupon Promotion | Customer | Customer checkout: Apply coupon discount codes for price deduction. | HoangDMHE191087 | III.7 | Done |  | 4 | 150
25 | Invoice & Billing | Generate Digital Invoice | System | System: Auto-generate digital invoice after successful payment. | HoangDMHE191087 | III.8 | Done |  | 3 | 120
26 | Order Returns & Refund Requests | Create Return/Exchange Request | Customer | Customer: Submit return/exchange requests with photo evidence. | HoangDMHE191087 | III.10 | Done |  | 4 | 150
27 | Customer Order History | View Order History Detail | Customer | Customer: View order history details, timeline, and invoice. | HoangDMHE191087 | III.11 | Done |  | 3 | 120
28 | Marketing Campaigns | Discount Coupons Creation | Shop Owner, Admin | Shop Owner: Create and manage promotional discount coupons. | HoangDMHE191087 | III.12 | Done |  | 4 | 150
|  | Seasonal Campaigns | Shop Owner, Admin | Shop Owner: Create automated seasonal discount campaigns. | HoangDMHE191087 | III.13 | Done |  | 4 | 150
|  | Flash Sales Configuration | Shop Owner, Admin | Shop Owner: Create timed Flash Sale events with limited stock. | HoangDMHE191087 | III.14 | Done |  | 4 | 150
29 | Product Review & Rating System | Write Product Review | Customer | Customer: Submit product reviews with ratings and image attachments. | Duong | III.15 | Done |  | 4 | 150
|  | Edit / Delete Product Review | Customer | Customer: Edit or delete personal product reviews and recalculate average. | Duong | III.16 | Done |  | 3 | 120
|  | Rate Products Stars | Customer | Customer: Interactive star-rating widget (1-5 stars) for reviews. | Duong | III.17 | Done |  | 1 | 60
|  | Average Rating Calculation | System | System: Automatically update average rating for products. | Duong | III.18 | Done |  | 2 | 90
|  | Approve/Reject Reviews | Admin | Admin: Review moderation panel to approve or block user reviews. | Duong | III.19 | Done |  | 3 | 120
30 | Notification & Alert Center | Order Confirmation | System | System: Send email and in-app notifications upon order creation. | Khang | III.20 | Done |  | 2 | 90
|  | Payment Notification | System | System: Send automated payment receipt notifications to customers. | Khang | III.21 | Done |  | 2 | 90
|  | Delivery Status Updates | System | System: Notify customers of shipping updates (Shipped/Delivered). | Khang | III.22 | Done |  | 2 | 90
|  | Promotion Notifications | Admin | Admin: Send promotional notifications to all customers in background. | Duong | III.23 | Done |  | 4 | 150
|  | Low Stock Warning | System | System: Warn Shop Owners when variant inventory falls below 5 items. | Khang | III.24 | Done |  | 2 | 90
|  | New Order Alert | System | System: Instant notification to Shop Owners on new order placement. | Khang | III.25 | Done |  | 3 | 120
|  | Email Notifications | System | System: General email sender service utilizing JavaMail API. | HoangDMHE191087 | III.26 | Done |  | 4 | 150
|  | In-App Notifications bell | Customer | Customer: Real-time notification badge and dropdown on header. | Khang | III.27 | Done |  | 3 | 120
31 | Global Admin Monitoring | Monitor Orders Global | Admin | Admin panel: Global order monitoring dashboard with multi-filters. | Duong | III.28 | Done |  | 4 | 150
|  | Monitor Payments Global | Admin | Admin panel: Monitor all transaction logs and VietQR bank transfers. | Duong | III.29 | Done |  | 4 | 150
|  | Handle Refund Requests | Admin | Admin panel: Review and approve customer refund requests. | Duong | III.30 | Done |  | 4 | 150
32 | Analytics & Reporting | Revenue Report Chart.js | Shop Owner, Admin | Shop/Admin: Revenue visualization charts powered by Chart.js. | Khang | III.31 | Done |  | 5 | 180
|  | Sales/Fruit Usage Report | Shop Owner, Admin | Shop/Admin: Advanced sales and fruit usage reports generation. | Khang | III.32 | Done |  | 6 | 210
|  | Order Statistics | Shop Owner, Admin | Shop/Admin: Order success and cancellation statistics charts. | Khang | III.33 | Done |  | 4 | 150
33 | Shop Settlement Batch Job | Shop Settlement Batch Job | System | System: Daily background job for auto-settlement of completed orders. | Khang | III.34 | Done |  | 7 | 240

## MetaFruit_Document
No. | Feature | Decriptions | Main actors | Description | In Charge | Status | Notes / Updates
SRS
1 | Context Diagram | Overall context |  |  | Hai | Done
|  | Context diagram |  |  | Hai | Done
[5 empty] | Hai | Done
2 | Main Business Processes | Order Processing |  |  | Hai | Done
|  | Shop owner onboarding |  |  | Hai | Done
|  | Manage Inventotry |  |  | Hai | Done
[5 empty] | Hai | Done
3 | User Requirements | Actors |  |  | Hai | Done
|  | Core Usecase List |  |  | Hoang | Done
|  | Usecase Diagram |  |  | Hai | Done
4 | System Functionalities | Non-UI Functions |  |  | Hai | Done
|  | Screen Authorization |  |  | Hai | Done
5 | Entity Relationship Diagram | Designing ERD and Creating Detailed Database Specifications |  |  | Hoang | Done
6 |  |  |  |  | Hoang | Done
[5 empty] | Hoang | Done
[5 empty] | Hoang | Done
[5 empty] | Hoang | Done
[5 empty] | Hoang | Done
7 | Use Case Specifications | Use case 1-8 |  |  | Hoang | Done
|  | Use case 9-14,31-40 |  |  | Duong | Done
|  | Use case 15-30 |  |  | Khang | Done
|  | Use case 40-50 |  |  | Hoang | Done
8 | Functional Requirements | Screen Mockups and Functional Requirements for Each Component |  |  | Hoang | Done
[5 empty] | Hoang | Done
[5 empty] | Hoang | Done
[5 empty] | Hoang | Done
[5 empty] | Hoang | Done
9 | Non-Functional Requirements | External Interfaces |  |  | Khang | Done
10 |  | Quality Attributes |  |  | Khang | Done
11 | Requirement Appendix | Bussiness Rules |  |  | Hoang | Done
|  | System messages |  |  | Duong | Done
|  | Other messages |  |  | Duong | Done
SDS
| Software Architecture |  |  |  | Hoang | Done
| Package Diagram |  |  |  | Hoang | Done
| Database Design |  |  |  | Hoang | Done
| Database Table Matrix |  |  |  | Hoang | Done
| State Transition Diagrams |  |  |  | Hoang | Done
| Detailed Design |  |  |  | Hoang | Done

## Iteration Plan
No. | Iteration 1 | Iteration 2 | Iteration 3
1 | User Registration Local Form | Add New Product | Cash on Delivery COD
2 | Google OAuth Sign-up | Edit Product Info | E-wallet VietQR Dynamic QR
3 | Role Selection | Delete Listing | Process Payment
4 | Local Login | Hide Listing | Payment Confirmation SePay Webhook
5 | Google OAuth Sign-in | Product Images CRUD | Real-time Status Polling
6 | User Logout | View Product Details | Payment Refund Logic
7 | Login Lockout | Weight Variants | Apply Coupon Promotion
8 | View Profile | Packaging Options | Generate Digital Invoice
9 | Edit Profile | Organic/Imported Labels | Create Return/Exchange Request
10 | Manage Addresses | Seasonal Availability | View Order History Detail
11 | Change Password | Stock Quantity Tracking | Discount Coupons Creation
12 | Role Management | Low Stock Alerts | Seasonal Campaigns
13 | View Product List | Restock Management | Flash Sales Configuration
14 | View Product Details | Base Pricing | Write Product Review
15 | Browse by Category | Discount Pricing | Edit / Delete Product Review
16 | Browse Featured Products | Filter Category | Rate Products Stars
17 | Search by Product Name | Filter Price | Average Rating Calculation
18 | Manage Customers | Filter Rating | Approve/Reject Reviews
19 | Manage Shop Owners | Filter Availability | Order Confirmation
20 | Block/Unblock Accounts | Sort Products | Payment Notification
21 | Approve Shop Owner Accounts | Recommended Fruits | Delivery Status Updates
22 |  | Best Sellers | Promotion Notifications
23 |  | Recently Viewed | Low Stock Warning
24 |  | Guest Cart LocalStorage | New Order Alert
25 |  | Customer Cart DB | Email Notifications
26 |  | Guest-Customer Cart Sync | In-App Notifications bell
27 |  | Update Quantity | Monitor Orders Global
28 |  | Remove Product | Monitor Payments Global
29 |  | Cart Summary | Handle Refund Requests
30 |  | Add to Wishlist | Revenue Report Chart.js
31 |  | Remove from Wishlist | Sales/Fruit Usage Report
32 |  | Move Wishlist to Cart | Order Statistics
33 |  | Select Delivery Address | Shop Settlement Batch Job
34 |  | Order Confirmation | Reset Password
35 |  | Create Order
36 |  | Reservate Inventory
37 |  | Reorder Previous Purchase
38 |  | Track Order Status
39 |  | Estimated Delivery Time
40 |  | Order Delivery Confirmation
41 |  | View Orders for Delivery
42 |  | Update Shipping Status
43 |  | Approve Order Shop Owner
44 |  | Reject Order Shop Owner
45 |  | Mark Order as Delivered
46 |  | Approve Products
47 |  | Remove Inappropriate Products
48 |  | Manage Categories CRUD

## Loc
Item | Failed | Normal Cases |  |  | Best Case | Notes
No of screens/functions | 4 | 5 | 6 | 7 | 8 | Tổng số screens/functions hoàn thiện đủ happy cases
Maximum LOC (C) | 480 | 600 | 720 | 840 | 960 | Số LOC quy đổi (L2-3-4 = 33%, 33%, 33%)
Quality Level (Q) | 50% | 50% | 75% | 75% | 75% | Chất lượng màn hình/chức năng**
Evaluated LOC | 240 | 300 | 540 | 630 | 720 | Số LOC đạt được (LOC = C*Q)
LOC Grade (LG) | 3.6364 | 4.5455 | 8.1818 | 9.5455 | 10.9091 | 70% | Tỷ trọng điểm LOC
Non-LOC Grade (Pkg) | 6 | 6 | 7 | 7 | 8 | 30% | Tỷ trọng điểm quy trình, material liên quan..
ĐIỂM ĐÁNH GIÁ (/10) | 4.3455 | 4.9818 | 7.8273 | 8.7818 | 10.0364
Converted LOC (for each of the complexity levels)
Complexity Level | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | Level 7 | Level | Fields | Trans* | LOC | Notes
Converted LOC | 60 | 90 | 120 | 150 | 180 | 210 | 240 | Level 1 | 3-5 | 2 | 60 | 3-5 fields OR 2 trans
[8 empty] | Level 2 | 6-7 | 3 | 90 | 6-7 fields OR 3 trans
Screen/Function Complexity Levels | [7 empty] | Level 3 | 8-9 | 4 | 120 | 8-9 fields OR 4 trans
Screen complexity can be defined based on the screen's fields OR screen/function's transactions | [7 empty] | Level 4 | 10-11 | 5 | 150 | 10-11 fields OR 5 trans
- Transactions can be counted as number of transactions to the database or external systems/subsystems | [7 empty] | Level 5 | 12-13 | 6 | 180 | 12-13 fields OR 6 trans
- Fields are screen's actionable components or database table fields; if there are some transactions those are | [7 empty] | Level 6 | 14-15 | 7 | 210 | 14-15 fields OR 7 trans
not "related" to any fields, each of those transactions are counted as two fields and add those extra number | [7 empty] | Level 7 | >15 | >7 | 240 | >15 fields OR >7 trans
to the total number of fields to define the screen/function complexity | [7 empty] | *One trans (transactions) = Two fields (actionable screen components)
Complexity Level | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | Level 7
No of transactions (to database, external,..) | 2 | 3 | 4 | 5 | 6 | 7 | >7
One transaction can be converted as two actionable fields
OR: no of fields | 3-5 | 6-7 | 8-9 | 10-11 | 12-13 | 14-15 | >15
Screen/Function Quality Levels & LOC Evaluation Rate
Level | Rate | Notes
L1_Happy Cases | 50% | The screen/function is workable, all happy cases are included
L2_All Cases | 75% | The screen/function is workable with both happy and unhappy cases included
L3_Optimized | 100% | All happy & unhappy cases included + the function/screen is optimized in term of UX and and business logics (suitability to real-world use cases)
Some samples of screen complexity defining are as following
Sample #1 | [7 empty] | Sample #2
Sample #3

## HoangDMHE191087
ITER1
ITER2
ITER3